## Sheet1
SAMPLE Five Year Strategic Plan for ___________________ MS STEM program This is only a small sample and the full chart for all five years should be filled in.
Year | Area | Description | Approximate Cost | Funding Source | Additional Information | Start Date | End Date
20**-20** | Curriculum/Technology Updates | Update 8 computers | 6400 | Grant application | If not approved will purchase in 2014-2015 school year with 412 funds | Fill out PO 8/15/2016, place order by 10/1/2013 | Computers arrived and installed by 01/01/2014
| Curriculum/Technology Updates | Implement new safety videos to reinforce high school | $45 online | Carl Perkins |  | Begin PO 7/15/2013 | Complete 2/1/2014
| Professional development | Robotics training | 2000 | 412 |  | 2014-07-01 | 2014-07-01
| Professional development | Summer Conference | 500 | 412 | Attend sessions on the design process and engineering notebooks | 2013-08-01 | 2013-08-02
| Budget development/utilization What percent of 412 is spent in each area | ___% - Equipment and Curriculum ___% - Consumables and supplies ___% - Professional Development |  | 412
| Facility renovation | Take out wall/add windows beween classroom and workroom so instructor can monitor both areas | 5000 | School funding |  | Planning from 10/01/2013 | Complete renovations summer 2014
| Business/Industry utilization | Tour _________ |  |  | Exposes students to engineering careers/exposes student to health care careers | Plan tour three months in advance | Tour 02/15/2014
| Business/Industry utilization | Partner with high school and technology centers |  |  |  | Ongoing | Ongoing
| Instructional materials | Integrate math/science concepts within _________ lesson | 0 | NA |  | 2013-09-01 | 2014-12-15
| Equipment and supplies acquisition | Purchase two VEX kits |  | 412
| Employability skills | Set up mock interviews over engineering careers | 0 | NA |  | Set up interviews 11/15/2014 | Interviews 12/10/2013
| Employability skills | Have students take interest invetory, set up coverletter, resume, and references | 0 | NA |  | Start 09/01/2013 | Complete by 04/01/2014
| Student organization | Attend TSA Nationals | 4000 | TSA Fundraiser | Make enough to pay for all students rooms at nationals | Begin fundraiser ideas 09/01/2013 | Attend nationals 06/21/2014
| Student organization | Host Saturday STEM camps | 100 | TSA Fundraiser | (will make $1000) | Planning starts 1/10/2013 | Camp 06/10/2014-06/15/2014
| Student organization | Penny drive for ACS | 0 | NA | Collete coins to donate to the state service project. Have class penny war to see who can raise the most. | Planning begins at 10/15/2013 officer meeting | Penny drive ends 03/15/2014
Year | Area | Description | Approximate Cost | Funding Source | Additional Information | Start Date | End Date
20**-20** | Curriculum/Technology Updates | Implement new coursework in 6th grade |  | Grant
| Curriculum/Technology Updates | Update 8 computers | 6400 | 412 | If grant is not approved from 2013-2014 year
| Curriculum/Technology Updates | Implement the new IPADS (25) for access to curriculum, resources and to Journal work. | 6500 | District Bond | Begin implementation PO request July 15, 2017 completion Feb. 1, 2018 | Submit PO 7/15/2014 | Complete 2/1/2015
| Professional development | Attend Project WET training | 500 | 412 | Bring environmental learning into the classroom
Budget development/utilization
| Facility renovation | Paint floor in work room | 500 | School Funding
| Business/Industry utilization | Hold a meeting in the fall and spring. Approve strategic plan. Update information on program, community, school and business/industry | 100 | Donations from committee | Approve request to main office by 7/15/2014, send out date and invitiations by 8/10/2014, second meeting invitations sent out by 3/28/2015 | Approve request by 7/15/2014 | 2015-05-01
Instructional materials
Equipment and supplies acquisition
| Employability skills | Set 2-4 professional business visits a semester and update to okcareerguide.com | 100 | Donations and activity account | Submit dates to principal, after approval make arrangments to complete. | 2014-07-01 | 2015-05-15
| Student organization | Attend eastern region fun day with at least 10 members | 200 | TSA Fundraiser
| Student organization | Participate in ACS Relay for Life event | 1200 | TSA Fundraiser/donations
| Student organization | Community service activity | 0 |  | Have at least 20 members participate in the park cleanup day for the community
Year | Area | Description | Approximate Cost | Funding Source | Additional Information | Start Date | End Date
20**-20** | Curriculum/Technology Updates
Professional development
Budget development/utilization
Facility renovation
Business/Industry utilization
Instructional materials
Equipment and supplies acquisition
Employability skills
Student organization
Year | Area | Description | Approximate Cost | Funding Source | Additional Information | Start Date | End Date
20**-20** | Curriculum/Technology Updates
Professional development
Budget development/utilization
Facility renovation
Business/Industry utilization
Instructional materials
Equipment and supplies acquisition
Employability skills
Student organization
Year | Area | Description | Approximate Cost | Funding Source | Additional Information | Start Date | End Date
20**-20** | Curriculum/Technology Updates
Professional development
Budget development/utilization
Facility renovation
Business/Industry utilization
Instructional materials
Equipment and supplies acquisition
Employability skills
Student organization
SAMPLE
SAMPLE
SAMPLE
SAMPLE
SAMPLE